AI x CITY CLIMATE ACTION HACKATHON 2026

EVSwap

6-Month Pilot Plan

AI-guided e-mobility charging/swap siting for Nairobi — from a ranked pipeline to built infrastructure serving over a million residents.

Submitted by:

Priscila Adhiambo — GIS Engineer / Urban Planner

Fauzia Omala — Software Engineer

Chibuike Nwafor — AI/ML Engineer

Benard Kimani — Software Engineer

Lynne Adhiambo — Urban Designer

# 1. Overview & Objective

This Pilot Plan operationalizes the top-20 site recommendations produced by the EVSwap need-analysis pipeline into built, physical e-mobility charging and swap infrastructure across Nairobi, over a 6-month period.

The pipeline has already identified, ranked, and phased these sites using verified population, transit-frequency, and existing-infrastructure data. This plan converts that ranked list into a concrete sequence of on-ground activities — site verification, stakeholder engagement, permitting, procurement, and installation — organized into three 2-month blocks aligned to the pipeline's own Phase 1 prioritization.

Primary objective: validate and begin construction on the 20 highest-need sites, directly serving an estimated 1,004,338 residents today (growing to ~1.19M by mid-2026), while proving the pipeline's replicability for future phases and other cities.

# 2. Team & Roles

A five-person core team, spanning the technical pipeline, the two decision-support applications (planner dashboard and EVSwap driver app), and on-ground urban design and planning liaison.

| Name | Role | Pilot Responsibilities |
| --- | --- | --- |
| Priscila Adhiambo | GIS Engineer / Urban Planner | Leads on-ground site verification for all 20 sites; liaises with Nairobi City County planning & transport departments on land tenure, zoning, and permitting; validates H3/GIS outputs against surveyed ground truth. |
| Fauzia Omala | Software Engineer | Maintains and hardens the OpenLayers/Kepler decision-support dashboard for county planner use; keeps the data pipeline (GTFS, WorldPop, infra refresh) reliable as new stations come online. |
| Chibuike Nwafor | AI/ML Engineer | Owns the need-score and growth-forecast models; refreshes LLM-generated site rationales as pilot data updates; monitors for model drift as verified infrastructure changes coverage_norm. |
| Benard Kimani | Software Engineer | Builds and deploys the EVSwap driver-facing app; integrates newly-verified pilot stations into live station data; manages the driver-facing beta and public release. |
| Lynne Adhiambo | Urban Designer | Leads community and stakeholder engagement at each site; develops placemaking/accessibility/safety guidelines for physical installations; coordinates resident and operator feedback sessions. |

# 3. 6-Month Timeline

The rollout follows the pipeline's own phasing: the 20 Phase-1 (“needed now”) sites are split into three 2-month blocks by need-score rank, so the highest-need, highest-population sites are validated and built first.

## Months 1–2 — 7 Sites (Highest Need)

Focus: partner alignment, ground-truthing the top-ranked sites, and hardening both applications ahead of scale.

- Kickoff & partner alignment: confirm engagement with Nairobi City County transport department and relevant operators (Roam, BasiGo, Ampersand) for the 7 highest-ranked sites.

- On-ground site verification survey for all 7 sites (Priscila) — confirm land availability, grid-connection feasibility, and land tenure against the pipeline's centroid recommendations.

- Community and stakeholder engagement sessions at each site (Lynne) — resident and operator feedback, informal-settlement input where applicable.

- Finalize siting specifications and submit permitting applications for the 7 sites.

- Harden the OpenLayers/Kepler decision-support dashboard for handoff to county planners (Fauzia); refresh the need-score model with any newly-verified infrastructure (Chibuike).

- Begin EVSwap driver-app build-out, integrating the first verified stations into live station data (Benard).

Milestone: 7 sites ground-truthed and permitted; dashboard handoff-ready; EVSwap alpha wired to real station data.

## Months 3–4 — 7 Sites (Continued)

Focus: procurement, construction start on the first block, and driver-app beta testing.

- Site verification and permitting for the next 7 ranked sites (Priscila).

- Procurement: identify and contract installation partners per infrastructure type — bus-charging depot, e-bike/motorcycle swap hub, or car charging point.

- Construction begins on the Months 1–2 sites as permits clear.

- Monitoring dashboard v1: track installation progress against the pipeline's ranked recommendations (Fauzia).

- LLM insight refresh incorporating updated growth and coverage data as the first stations come online (Chibuike).

- EVSwap driver-app beta test with a small cohort of e-bike and matatu drivers in the Phase-1 corridor (Benard, with Lynne on user feedback).

Milestone: construction underway on Months 1–2 sites; 14 of 20 sites verified and permitted; EVSwap in closed beta.

## Months 5–6 — 6 Sites (Completion)

Focus: complete the full 20-site rollout, launch both applications publicly, and report on pilot outcomes.

- Site verification and permitting for the final 6 ranked sites (Priscila).

- Construction completes across all 20 sites.

- Cross-phase impact review: compare predicted need/coverage against actual installed infrastructure and early usage data.

- Public launch of the decision-support dashboard for Nairobi City County planning use (Fauzia).

- EVSwap public release within the pilot corridor (Benard).

- Final pilot report and handoff package prepared for scaling to Phase 2/3 hexagons — or replication in another city (all team members).

Milestone: all 20 sites verified, permitted, and under or complete construction; both applications publicly live; final pilot report delivered.

# 4. Milestones & Deliverables

| Period | Deliverable | Owner(s) |
| --- | --- | --- |
| Months 1–2 | 7 sites ground-truthed & permitted; dashboard handoff-ready; EVSwap wired to real data | Priscila, Fauzia, Chibuike, Benard, Lynne |
| Months 3–4 | 14/20 sites verified; construction started on first block; EVSwap closed beta | Priscila, Fauzia, Chibuike, Benard |
| Months 5–6 | All 20 sites complete or under construction; public dashboard + EVSwap launch; final report | Full team |

# 5. Success Metrics

Kept to what the pipeline and pilot can actually measure — no unsourced emissions or ridership estimates.

- Sites recommended vs. sites successfully sited (target: 20/20 Phase-1 sites permitted, 6-month horizon).

- Residents within service catchment of newly-sited infrastructure (baseline: 1,004,338 today, ~1.19M projected by mid-2026).

- EVSwap driver-app adoption within the pilot corridor (beta cohort size, public release download/usage count).

- Decision-support dashboard adoption by county planning staff (active users, sessions).

- Data pipeline reproducibility: time-to-first-output when re-run against a second city's open data (replicability proof point).

# 6. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Land tenure / permitting delays | Site construction slips past the 6-month window | Early, parallel engagement with county departments starting Month 1; permitting begins before construction procurement |
| Underlying data goes stale (WorldPop, GTFS updates) | Need-score rankings drift from ground reality | Pipeline is scripted and versioned end-to-end; re-run steps 01–15 against refreshed source data at each 2-month checkpoint |
| Operator coordination (Roam, BasiGo, Ampersand, etc.) | Installation partner availability bottlenecks a site | Named-operator outreach begins Month 1; procurement in Months 3–4 spreads sites across multiple operators by infrastructure type |
| Funding gap for full 20-site build-out | Pilot completes fewer than 20 sites in 6 months | Phased ask allows partial funding to still complete Months 1–2 sites; pursue matched funding via UTM city-pairing and C40 coalition partners |

# 7. The Ask

Pilot funding and partnership to validate and build the top 20 Phase-1 sites over 6 months — turning a ranked, AI-assisted siting analysis into physical infrastructure serving over a million Nairobi residents, and a proven, replicable methodology for the next city.